## Sprint 1
Project Name | OLMTSystem
Module Name | Sprint 1
Development Team | C1SE.23
Start Date | 2023-09-08
End Date | 2023-09-27
| Sprint 1 Report | [19 empty] | Kết thúc nhiệm vụ
| No. | Member Name | Estimate | Actual | [16 empty] | Giờ làm thêm
| 1 | Ho Minh Khanh | 67 | 80 | [16 empty] | Trễ
| 2 | Nguyen Duy Trinh | 65 | 77 | [16 empty] | Chậm tiến độ
| 3 | Pham Tan Dat | 60 | 75 | [16 empty] | Trước thời hạn
| 4 | Nguyen Van Sy | 58 | 71
| Total |  | 251 | 303
Estimate
Sprint 1 | Component | Task Name | Responsible Member | Estimate | Total | 2023-09-08 | 2023-09-09 | 2023-09-10 | 2023-09-11 | 2023-09-12 | 2023-09-13 | 2023-09-14 | 2023-09-15 | 2023-09-16 | 2023-09-17 | 2023-09-18 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 | 2023-09-27
| Initial | Sprint Plan Meeting | Khanh,Trinh,Sy,Dat | 4 | 4 | 0
|  | Sprint Backlog for sprint 1 | Khanh | 8 | 8 | 4 | 0
|  | User Interface for sprint 1 | Trinh | 8 | 8 | 4 | 0
|  | Test Plan for sprint 1 | Dat | 4 | 4 | 4 | 0
|  | Test Case for sprint 1 | Sy | 8 | 8 | 4 | 0
|  | Create Database Design for sprint1 | Khanh | 8 | 8 | 8 | 4 | 0
|  | Create Architecture Design for sprint1 | Sy, Trinh | 16 | 16 | 16 | 8 | 0
| Design UI | Design UI of “ Login” | Sy | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “ Register” | Dat | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Homepage Admin” | Khanh | 4 | 4 | 4 | 4 | 4 | 0
|  | Design UI of “Homepage Instructor” | Trinh | 4 | 4 | 4 | 4 | 4 | 0
|  | Design UI of “Homepage Student” | Khanh | 4 | 4 | 4 | 4 | 4 | 0
|  | Design UI of “View Personal information” | Khanh | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Edit Personal information” | Trinh | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Design Testcase | Design Testcase of “ Login” | Sy | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  | Design Testcase of “ Register” | Dat | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  | Design Testcase of “Homepage Admin” | Sy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Design Testcase of “Homepage Instructor” | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Design Testcase of “Homepage Student” | Sy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Design Testcase of “View Personal information” | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Design Testcase of “Edit Personal information” | Sy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Code | Code UI of “ Login” | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “ Register” | Sy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “Homepage Admin" | Khanh | 8 | 8 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Code UI of “Homepage Instructor" | Trinh | 8 | 8 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code UI of “Homepage Student” | Khanh | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | Code UI of “View Personal information” | Khanh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code UI of “Edit Personal information” | Trinh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Code [Back-end] of “ Login” | Trinh, Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Code [Back-end] of “Register” | Khanh, Sy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Code [Back-end] of “Homepage Admin” | Khanh | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Code [Back-end] of “Homepage Instructor” | Khanh | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Code [Back-end] of “Homepage Student” | Trinh | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Code [Back-end] of “View Personal information” | Khanh | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code [Back-end] of “Edit Personal information” | Trinh | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Integration | Integration for sprint 1 | Khanh, Trinh | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 6 | 0
| Testing | Test feature “Login” | Trinh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature "Register" | Sy | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “View Homepage Admin” | Khanh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “View Homepage Instructor” | Dat | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “View Homepage Student” | Dat | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “View Personal Information” | Sy | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature "Edit Personal Information" | Dat | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Sprint 1 Review Meetying | Sprint 1 Review Meeting | Khanh,Trinh,Sy,Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Release Sprint 1 | Release Sprint 1 | Khanh,Trinh,Sy,Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Searching | Technology | Khanh,Trinh,Sy,Dat | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
|  |  | Total | 251 | 251 | 227 | 199 | 187 | 167 | 157 | 137 | 117 | 106 | 90 | 82 | 66 | 54 | 48 | 40 | 38 | 36 | 32 | 28 | 8 | 0
Actual
Sprint 1 | Component | Task Name | Responsible Member | Actual | Total | 2023-09-08 | 2023-09-09 | 2023-09-10 | 2023-09-11 | 2023-09-12 | 2023-09-13 | 2023-09-14 | 2023-09-15 | 2023-09-16 | 2023-09-17 | 2023-09-18 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-23 | 2023-09-24 | 2023-09-25 | 2023-09-26 | 2023-09-27
| Initial | Sprint Plan Meeting | Khanh,Trinh,Sy,Dat | 4 | 4 | 0
|  | Sprint Backlog for sprint 1 | Khanh | 8 | 8 | 4 | 0
|  | User Interface for sprint 1 | Trinh | 8 | 8 | 4 | 0
|  | Test Plan for sprint 1 | Dat | 4 | 4 | 4 | 4 | 0
|  | Test Case for sprint 1 | Sy | 8 | 8 | 4 | 4 | 0
|  | Create Database Design for sprint1 | Khanh | 8 | 8 | 8 | 4 | 0
|  | Create Architecture Design for sprint1 | Sy, Trinh | 16 | 16 | 16 | 8 | 0
| Design UI | Design UI of “ Login” | Sy | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “ Register” | Dat | 2 | 2 | 2 | 2 | 2 | 0
|  | Design UI of “Homepage Admin” | Khanh | 4 | 4 | 4 | 4 | 4 | 0
|  | Design UI of “Homepage Instructor” | Trinh | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Design UI of “Homepage Student” | Khanh | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Design UI of “View Personal information” | Khanh | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Edit Personal information” | Trinh | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Design Testcase | Design Testcase of “ Login” | Sy | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  | Design Testcase of “ Register” | Dat | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  | Design Testcase of “Homepage Admin” | Sy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Design Testcase of “Homepage Instructor” | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Design Testcase of “Homepage Student” | Sy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Design Testcase of “View Personal information” | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Design Testcase of “Edit Personal information” | Sy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Code | Code UI of “ Login” | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Code UI of “ Register” | Sy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
|  | Code UI of “Homepage Admin" | Khanh | 8 | 8 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Code UI of “Homepage Instructor" | Trinh | 8 | 8 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0
|  | Code UI of “Homepage Student” | Khanh | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | Code UI of “View Personal information” | Khanh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code UI of “Edit Personal information” | Trinh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Code [Back-end] of “ Login” | Trinh, Dat | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 4 | 0
|  | Code [Back-end] of “Register” | Khanh, Sy | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 4 | 0
|  | Code [Back-end] of “Homepage Admin” | Khanh | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
|  | Code [Back-end] of “Homepage Instructor” | Khanh | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 4 | 0
|  | Code [Back-end] of “Homepage Student” | Trinh | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 4 | 0
|  | Code [Back-end] of “View Personal information” | Khanh | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Code [Back-end] of “Edit Personal information” | Trinh | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
| Integration | Integration for sprint 1 | Khanh, Trinh | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 12 | 6 | 0
| Testing | Test feature “Login” | Trinh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature "Register" | Sy | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “View Homepage Admin” | Khanh | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “View Homepage Instructor” | Dat | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “View Homepage Student” | Dat | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature “View Personal Information” | Sy | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | Test feature "Edit Personal Information" | Dat | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Sprint 1 Review Meetying | Sprint 1 Review Meeting | Khanh,Trinh,Sy,Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Release Sprint 1 | Release Sprint 1 | Khanh,Trinh,Sy,Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Searching | Technology | Khanh,Trinh,Sy,Dat | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
|  |  | Total | 303 | 303 | 279 | 259 | 239 | 227 | 209 | 197 | 173 | 165 | 142 | 126 | 94 | 82 | 54 | 48 | 40 | 36 | 36 | 32 | 12 | 0
[5 empty] | Estimate | 2022-09-08 | 2022-09-09 | 2022-09-10 | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-25 | 2022-09-26 | 2022-09-27
|  |  |  | Estimate | 251 | 227 | 199 | 187 | 167 | 157 | 137 | 117 | 106 | 90 | 82 | 66 | 54 | 48 | 40 | 38 | 36 | 32 | 28 | 8 | 0
|  |  |  | Actual | 303 | 279 | 259 | 239 | 227 | 209 | 197 | 173 | 165 | 142 | 126 | 94 | 82 | 54 | 48 | 40 | 36 | 36 | 32 | 12 | 0

## Sprint 2
Project Name | OLMTSystem
Module Name | Sprint 2
Development Team | C1SE.23
Start Date | 2023-09-28
End Date | 2023-10-22 | [13 empty] | Kết thúc nhiệm vụ
Giờ làm thêm
| Sprint 2 Report | [13 empty] | Trễ
| No. | Member Name | Estimate | Actual | [10 empty] | Chậm tiến độ
| 1 | Ho Minh Khanh | 63 | 80 | [10 empty] | Trước thời hạn
| 2 | Nguyen Duy Trinh | 63 | 78
| 3 | Pham Tan Dat | 63 | 76
| 4 | Nguyen Van Sy | 63 | 73
| Total |  | 252 | 307
Estimate
Sprint 2 | Component | Task Name | Responsible Member | Estimate | Total | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22
| Initial | Sprint Plan Meeting | Khanh,Trinh,Sy,Dat | 16 | 16 | 0
|  | Sprint Backlog for sprint 2 | Khanh | 4 | 4 | 4 | 0
|  | User Interface for sprint 2 | Trinh | 4 | 4 | 4 | 0
|  | Test Plan for sprint 2 | Dat | 4 | 4 | 4 | 0
|  | Create Database Design for sprint2 | Sy | 4 | 4 | 4 | 4 | 2 | 0
|  | Test Case for sprint 2 | Khanh | 4 | 4 | 4 | 4 | 2 | 0
|  | CreateArchitecture Design for sprint2 | Sy, Trinh | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
| Design UI | Design UI of “News Page” | Khanh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Management Account” | Trinh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Management Course” | Dat | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Management News ” | Sy | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Design Testcase | Design Testcase of “ Login for admin” | Sy | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design Testcase of “ Logout for admin” | Dat | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design Testcase of “Management Account” | Sy | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design Testcase of “Management Course” | Dat | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design Testcase of “Management News” | Sy | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design Testcase of “Create News” | Dat | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Code | Code UI of “News Page” | Khanh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
|  | Code UI of “Management Account” | Trinh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
|  | Code UI of “Management Course” | Trinh, Dat | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
|  | Code UI of “Management News” | Khanh, Sy | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
|  | Code [Back-end] of “ Login for admin” | Khanh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
|  | Code [Back-end] of “ Logout for admin” | Khanh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code [Back-end] of “News Page” | Trinh | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 0
|  | Code [Back-end] of “Management Account” | Khanh | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0
|  | Code [Back-end] of “Management Course” | Trinh | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0
|  | Code [Back-end] of “Management News” | Khanh | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 0
| Integration | Integration for sprint 2 | Khanh, Trinh | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
| Testing | Test feature “Login for admin” | Trinh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Test feature "Logout for admin" | Sy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Test feature “News Page” | Khanh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Test feature “Management Account” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Test feature “Management Course” | Sy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Test feature “Management News” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
| Sprint 2 Review Meetying | Sprint 2 Review Meeting | Khanh,Trinh,Sy,Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Release Sprint 2 | Release Sprint 2 | Khanh,Trinh,Sy,Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Searching | Technology | Khanh,Trinh,Sy,Dat | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | Total | 252 | 252 | 236 | 224 | 220 | 216 | 208 | 200 | 172 | 163 | 154 | 140 | 126 | 114 | 112 | 104 | 99 | 94 | 81 | 76 | 74 | 66 | 54 | 42 | 16 | 8 | 0
Actual
Sprint 2 | Component | Task Name | Responsible Member | Actual | Total | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22
| Initial | Sprint Plan Meeting | Khanh,Trinh,Sy,Dat | 16 | 16 | 0
|  | Sprint Backlog for sprint 2 | Khanh | 4 | 4 | 4 | 0
|  | User Interface for sprint 2 | Trinh | 4 | 4 | 4 | 0
|  | Test Plan for sprint 2 | Dat | 4 | 4 | 4 | 0
|  | Create Database Design for sprint2 | Sy | 4 | 4 | 4 | 4 | 2 | 0
|  | Test Case for sprint 2 | Khanh | 4 | 4 | 4 | 4 | 2 | 0
|  | CreateArchitecture Design for sprint2 | Sy, Trinh | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
| Design UI | Design UI of “News Page” | Khanh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Management Account” | Trinh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Management Course” | Dat | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Management News ” | Sy | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Design Testcase | Design Testcase of “ Login for admin” | Sy | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design Testcase of “ Logout for admin” | Dat | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design Testcase of “Management Account” | Sy | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design Testcase of “Management Course” | Dat | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design Testcase of “Management News” | Sy | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design Testcase of “Create News” | Dat | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Code | Code UI of “News Page” | Khanh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
|  | Code UI of “Management Account” | Trinh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
|  | Code UI of “Management Course” | Trinh, Dat | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
|  | Code UI of “Management News” | Khanh, Sy | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
|  | Code [Back-end] of “ Login for admin” | Khanh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
|  | Code [Back-end] of “ Logout for admin” | Khanh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code [Back-end] of “News Page” | Trinh | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 10
|  | Code [Back-end] of “Management Account” | Khanh | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 8
|  | Code [Back-end] of “Management Course” | Trinh | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 8
|  | Code [Back-end] of “Management News” | Khanh | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15
| Integration | Integration for sprint 2 | Khanh, Trinh | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 8
| Testing | Test feature “Login for admin” | Trinh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 3
|  | Test feature "Logout for admin" | Sy | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 3
|  | Test feature “News Page” | Khanh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 3
|  | Test feature “Management Account” | Dat | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 3
|  | Test feature “Management Course” | Sy | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 3
|  | Test feature “Management News” | Dat | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| Sprint 2 Review Meetying | Sprint 2 Review Meeting | Khanh,Trinh,Sy,Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Release Sprint 2 | Release Sprint 2 | Khanh,Trinh,Sy,Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Searching | Technology | Khanh,Trinh,Sy,Dat | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | Total | 307 | 307 | 291 | 279 | 275 | 271 | 263 | 255 | 227 | 218 | 209 | 195 | 181 | 169 | 164 | 159 | 144 | 137 | 116 | 109 | 96 | 81 | 74 | 55 | 38 | 16 | 0
|  | Estimate | 2023-09-28 | 2023-09-29 | 2023-09-30 | 2023-10-01 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-07 | 2023-10-08 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-14 | 2023-10-15 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22
| Estimate | 252 | 236 | 224 | 220 | 216 | 208 | 200 | 172 | 163 | 154 | 140 | 126 | 114 | 112 | 104 | 99 | 94 | 81 | 76 | 74 | 66 | 54 | 42 | 16 | 8 | 0
| Actual | 307 | 291 | 279 | 275 | 271 | 263 | 255 | 227 | 218 | 209 | 195 | 181 | 169 | 164 | 159 | 144 | 137 | 116 | 109 | 96 | 81 | 74 | 55 | 38 | 16 | 0
Formulas:
Actual = [Estimate]+1

## Sprint 3
Project Name | OLMTSystem
Module Name | Sprint 3
Development Team | C1SE.23
Start Date | 2023-10-18
End Date | 2023-11-11
Sprint 3 Report
| No. | Member Name | Estimate | Actual
| 1 | Ho Minh Khanh | 69 | 86
| 2 | Nguyen Duy Trinh | 69 | 84
| 3 | Pham Tan Dat | 69 | 83
| 4 | Nguyen Van Sy | 69 | 80
| Total |  | 276 | 333
Estimate
Sprint 3 | Component | Task Name | Responsible Member | Estimate | Total | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11
| Initial | Sprint Plan Meeting | Khanh,Trinh,Sy,Dat | 16 | 16 | 0
|  | Sprint Backlog for sprint 3 | Khanh | 4 | 4 | 4 | 0
|  | User Interface for sprint 3 | Trinh | 4 | 4 | 4 | 0
|  | Test Plan for sprint 3 | Dat | 4 | 4 | 4 | 0
|  | Create Database Design for sprint 3 | Sy | 4 | 4 | 4 | 4 | 2 | 0
|  | Test Case for sprint 3 | Khanh | 4 | 4 | 4 | 4 | 2 | 0
|  | CreateArchitecture Design for sprint 3 | Sy, Trinh | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
| Design UI | Design UI of “Route Page” | Khanh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Lesson Page” | Trinh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Management Lesson” | Dat | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Face Recognition ” | Sy | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Assignment” | Khanh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Design Testcase | Design Testcase of “ Login for instructor” | Sy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “ Logout for instructor” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Route Page” | Sy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Lesson Page” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Management Lesson” | Sy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Face Recognition” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Assignment” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
| Code | Code UI of “Route Page” | Khanh | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | Code UI of “Lesson Page” | Trinh | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | Code UI of “Management Lesson” | Trinh, Dat | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | Code UI of “Face Recognition” | Khanh, Sy | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | Code UI of “Assignment” | Khanh | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
|  | Code [Back-end] of “ Login for instructor” | Khanh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code [Back-end] of “ Logout for instructor” | Trinh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code [Back-end] of “Route Page” | Khanh | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | Code [Back-end] of “Lesson Page” | Trinh | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | Code [Back-end] of “Face Recognition” | Khanh | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 6 | 0
|  | Code [Back-end] of “Management Lesson” | Trinh, Dat | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | Code [Back-end] of “Assignment” | Khanh, Sy | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 6 | 0
| Integration | Integration for sprint 3 | Khanh,Trinh,Sy,Dat | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
| Testing | Test feature “Login for instructor” | Trinh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Test feature "Logout for instructor” | Sy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Test feature “Route Page” | Khanh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Test feature “Lesson Page” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Test feature “Management Lesson” | Sy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Test feature “Face Recognition” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
| Sprint 3 Review Meetying | Sprint 3 Review Meeting | Khanh,Trinh,Sy,Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Release Sprint 3 | Release Sprint 3 | Khanh,Trinh,Sy,Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Searching | Technology | Khanh,Trinh,Sy,Dat | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | Total | 276 | 276 | 260 | 248 | 244 | 240 | 232 | 224 | 215 | 209 | 195 | 174 | 156 | 144 | 134 | 114 | 102 | 96 | 90 | 78 | 72 | 66 | 54 | 42 | 24 | 8 | 0
Actual
Sprint 3 | Component | Task Name | Responsible Member | Estimate | Total | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11
| Initial | Sprint Plan Meeting | Khanh,Trinh,Sy,Dat | 16 | 16 | 0
|  | Sprint Backlog for sprint 3 | Khanh | 4 | 4 | 4 | 0
|  | User Interface for sprint 3 | Trinh | 4 | 4 | 4 | 0
|  | Test Plan for sprint 3 | Dat | 4 | 4 | 4 | 0
|  | Create Database Design for sprint 3 | Sy | 4 | 4 | 4 | 4 | 2 | 0
|  | Test Case for sprint 3 | Khanh | 4 | 4 | 4 | 4 | 2 | 0
|  | CreateArchitecture Design for sprint 3 | Sy, Trinh | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
| Design UI | Design UI of “Route Page” | Khanh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Lesson Page” | Trinh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Management Lesson” | Dat | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Face Recognition ” | Sy | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Assignment” | Khanh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Design Testcase | Design Testcase of “ Login for instructor” | Sy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “ Logout for instructor” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Route Page” | Sy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Lesson Page” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Management Lesson” | Sy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Face Recognition” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Assignment” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
| Code | Code UI of “Route Page” | Khanh | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4
|  | Code UI of “Lesson Page” | Trinh | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4
|  | Code UI of “Management Lesson” | Trinh, Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4
|  | Code UI of “Face Recognition” | Khanh, Sy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4
|  | Code UI of “Assignment” | Khanh | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4
|  | Code [Back-end] of “ Login for instructor” | Khanh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
|  | Code [Back-end] of “ Logout for instructor” | Trinh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
|  | Code [Back-end] of “Route Page” | Khanh | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 14
|  | Code [Back-end] of “Lesson Page” | Trinh | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 14
|  | Code [Back-end] of “Face Recognition” | Khanh | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 14
|  | Code [Back-end] of “Management Lesson” | Trinh, Dat | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15
|  | Code [Back-end] of “Assignment” | Khanh, Sy | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15
| Integration | Integration for sprint 3 | Khanh,Trinh,Sy,Dat | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 10 |  | 0
| Testing | Test feature “Login for instructor” | Trinh | 5 | 5 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
|  | Test feature "Logout for instructor” | Sy | 5 | 5 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 3
|  | Test feature “Route Page” | Khanh | 5 | 5 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 3
|  | Test feature “Lesson Page” | Dat | 5 | 5 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 3
|  | Test feature “Management Lesson” | Sy | 5 | 5 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 3
|  | Test feature “Face Recognition” | Dat | 5 | 5 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 3
| Sprint 3 Review Meetying | Sprint 3 Review Meeting | Khanh,Trinh,Sy,Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4
| Release Sprint 3 | Release Sprint 3 | Khanh,Trinh,Sy,Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Searching | Technology | Khanh,Trinh,Sy,Dat | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | Total | 333 | 333 | 317 | 317 | 313 | 309 | 301 | 293 | 284 | 278 | 264 | 243 | 231 | 211 | 189 | 175 | 155 | 135 | 121 | 116 | 101 | 96 | 76 | 66 | 39 | 12 | 0
[5 empty] | Estimate | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-21 | 2023-10-22 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-28 | 2023-10-29 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-04 | 2023-11-05 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-11
|  |  |  | Estimate | 276 | 260 | 248 | 244 | 240 | 232 | 224 | 215 | 209 | 195 | 174 | 156 | 144 | 134 | 114 | 102 | 96 | 90 | 78 | 72 | 66 | 54 | 42 | 24 | 8 | 0
|  |  |  | Actual | 333 | 317 | 317 | 313 | 309 | 301 | 293 | 284 | 278 | 264 | 243 | 231 | 211 | 189 | 175 | 155 | 135 | 121 | 116 | 101 | 96 | 76 | 66 | 39 | 12 | 0

## Sprint 4
Project Name | OLMTSystem
Module Name | Sprint 4
Development Team | C1SE.23
Start Date | 2023-11-10
End Date | 25-thg 12-23
Sprint 4 Report
| No. | Member Name | Estimate | Actual
| 1 | Ho Minh Khanh | 70 | 97
| 2 | Nguyen Duy Trinh | 70 | 97
| 3 | Pham Tan Dat | 70 | 97
| 4 | Nguyen Van Sy | 69 | 97
| Total |  | 279 | 388
Estimate
Sprint 4 | Component | Task Name | Responsible Member | Estimate | Total | 2023-11-10 | 2023-11-11 | 2023-11-12 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-04
| Initial | Sprint Plan Meeting | Khanh,Trinh,Sy,Dat | 16 | 16 | 0
|  | Sprint Backlog for sprint 4 | Khanh | 4 | 4 | 4 | 0
|  | User Interface for sprint 4 | Trinh | 4 | 4 | 4 | 0
|  | Test Plan for sprint 4 | Dat | 4 | 4 | 4 | 0
|  | Create Database Design for sprint 4 | Sy | 4 | 4 | 4 | 4 | 2 | 0
|  | Test Case for sprint 4 | Khanh | 4 | 4 | 4 | 4 | 2 | 0
|  | CreateArchitecture Design for sprint 4 | Sy, Trinh | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
| Design UI | Design UI of “Management Assignment” | Khanh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Management Score" | Trinh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Score ” | Dat | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “My course” | Sy | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design UI of “Warning function ” | Khanh | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
| Design Testcase | Design Testcase of “ Login for student” | Sy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “ Logout for student” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Management Assignment” | Sy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Management Score” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Register Course ” | Sy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Warning function” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Face Recognition” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
| Code | Code UI of “Management Assignment” | Khanh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code UI of “Management Score” | Trinh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code UI of “Register Course ” | Trinh, Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code UI of “Warning function” | Khanh, Sy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code [Back-end] of “ Warning function” | Khanh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code [Back-end] of “ Monitoring on webcam function” | Khanh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code [Back-end] of “Monitoring action on the website function” | Trinh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Code [Back-end] of “Block copy/paste function” | Khanh | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
|  | Code [Back-end] of “Management Assignment” | Trinh | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 6 | 0
|  | Code [Back-end] of “Management Score” | Khanh | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 6 | 0
|  | Code [Back-end] of “Register Course” | Trinh, Dat | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 6 | 0
|  | Code [Back-end] of “Face Recognition” | Khanh, Sy | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 8 | 0
| Integration | Integration for sprint 4 | Khanh,Trinh,Sy,Dat | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 0
| Testing | Test feature “Warning function” | Trinh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Test feature "Monitoring on webcam function" | Sy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Test feature “Block copy/paste function” | Khanh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Test feature “Monitoring action on the website function” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Test feature “Management Assignment” | Sy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Test feature “Management Score” | Trinh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Test feature “Face Recognition” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
| Sprint 4 Review Meetying | Sprint 4 Review Meeting | Khanh,Trinh,Sy,Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Release Sprint 4 | Release Sprint 4 | Khanh,Trinh,Sy,Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Searching | Technology | Khanh,Trinh,Sy,Dat | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  |  | Total | 279 | 279 | 263 | 251 | 247 | 243 | 235 | 227 | 221 | 212 | 198 | 177 | 167 | 144 | 116 | 110 | 110 | 104 | 92 | 86 | 79 | 71 | 51 | 37 | 16 | 8 | 0
Estimate
Sprint 4 | Component | Task Name | Responsible Member | Estimate | Total | 2023-11-10 | 2023-11-11 | 2023-11-12 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-09 | 2023-12-10 | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | 2023-12-16 | 2023-12-17 | 2023-12-18 | 2023-12-19 | 2023-12-20 | 2023-12-21 | 2023-12-22 | 2023-12-23 | 2023-12-24 | 2023-12-25
| Initial | Sprint Plan Meeting | Khanh,Trinh,Sy,Dat | 16 | 16 | 0
|  | Sprint Backlog for sprint 4 | Khanh | 4 | 4 | 4 | 0
|  | User Interface for sprint 4 | Trinh | 4 | 4 | 4 | 0
|  | Test Plan for sprint 4 | Dat | 4 | 4 | 4 | 0
|  | Create Database Design for sprint 4 | Sy | 4 | 4 | 4 | 4 | 2 | 0
|  | Test Case for sprint 4 | Khanh | 4 | 4 | 4 | 4 | 2 | 0
|  | CreateArchitecture Design for sprint 4 | Sy, Trinh | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
| Design UI | Design UI of “Management Assignment” | Khanh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Design UI of “Management Score" | Trinh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0
|  | Design UI of “Score ” | Dat | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design UI of “My course” | Sy | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design UI of “Warning function ” | Khanh | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
| Design Testcase | Design Testcase of “ Login for student” | Sy | 7 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “ Logout for student” | Dat | 7 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Management Assignment” | Sy | 7 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Management Score” | Dat | 7 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Register Course ” | Sy | 7 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Warning function” | Dat | 7 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
|  | Design Testcase of “Face Recognition” | Dat | 7 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0
| Code | Code UI of “Management Assignment” | Khanh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
|  | Code UI of “Management Score” | Trinh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
|  | Code UI of “Register Course ” | Trinh, Dat | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
|  | Code UI of “Warning function” | Khanh, Sy | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
|  | Code [Back-end] of “ Warning function” | Khanh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0
|  | Code [Back-end] of “ Monitoring on webcam function” | Khanh | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0
|  | Code [Back-end] of “Monitoring action on the website function” | Trinh | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0
|  | Code [Back-end] of “Block copy/paste function” | Khanh | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 16 | 12 | 4 | 0
|  | Code [Back-end] of “Management Assignment” | Trinh | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 16 | 8 | 0
|  | Code [Back-end] of “Management Score” | Khanh | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 16 | 8 | 0
|  | Code [Back-end] of “Register Course” | Trinh, Dat | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 16 | 8 | 0
|  | Code [Back-end] of “Face Recognition” | Khanh, Sy | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 20 | 15 | 10 | 5 | 0
| Integration | Integration for sprint 4 | Khanh,Trinh,Sy,Dat | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 16 | 8 | 0
| Testing | Test feature “Warning function” | Trinh | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
|  | Test feature "Monitoring on webcam function" | Sy | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
|  | Test feature “Block copy/paste function” | Khanh | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0
|  | Test feature “Monitoring action on the website function” | Dat | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 0
|  | Test feature “Management Assignment” | Sy | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 0
|  | Test feature “Management Score” | Trinh | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 0
|  | Test feature “Face Recognition” | Dat | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 0
| Sprint 4 Review Meetying | Sprint 4 Review Meeting | Khanh,Trinh,Sy,Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
| Release Sprint 4 | Release Sprint 4 | Khanh,Trinh,Sy,Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
| Searching | Technology | Khanh,Trinh,Sy,Dat | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  |  | Total | 388 | 388 | 358 | 346 | 342 | 338 | 330 | 322 | 306 | 297 | 283 | 262 | 248 | 219 | 211 | 203 | 191 | 187 | 175 | 159 | 139 | 118 | 105 | 100 | 95 | 86 | 78 | 70 | 64 | 52 | 40 | 24 | 20 | 16 | 12 | 8 | 4 | 0
|  | Estimate | 2023-11-10 | 2023-11-11 | 2023-11-12 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-18 | 2023-11-19 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-25 | 2023-11-26 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-09 | 2023-12-10 | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | 2023-12-16 | 2023-12-17 | 2023-12-18 | 2023-12-19 | 2023-12-20 | 2023-12-21 | 2023-12-22 | 2023-12-23 | 2023-12-24 | 2023-12-25
| Estimate | 279 | 263 | 251 | 247 | 243 | 235 | 227 | 221 | 212 | 198 | 177 | 167 | 144 | 116 | 110 | 110 | 104 | 92 | 86 | 79 | 71 | 51 | 37 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual | 388 | 358 | 346 | 342 | 338 | 330 | 322 | 306 | 297 | 283 | 262 | 248 | 219 | 211 | 203 | 191 | 187 | 175 | 159 | 139 | 118 | 105 | 100 | 95 | 86 | 78 | 70 | 64 | 52 | 40 | 24 | 20 | 16 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Actual = [Estimate]+1